## 01 PA Overview
SHIFTManager • PA overview + Gantt
Project Title | Factory-team shift planning ¦ PA1–PA5
Project Manager | Nguyễn Huy Hoàng (Team 6)
Company Name | HCMUS • 404NotFound | [5 empty] | PA1 | [13 empty] | PA2 | [9 empty] | PA3 | [9 empty] | PA4 | [9 empty] | PA5 | [9 empty] | Final*
Date | 2026-10-19 | [5 empty] | 05 Oct |  |  |  |  | 12 Oct |  |  |  |  | 19 Oct |  |  |  |  | 26 Oct |  |  |  |  | 02 Nov |  |  |  |  | 09 Nov |  |  |  |  | 16 Nov |  |  |  |  | 23 Nov |  |  |  |  | 30 Nov |  |  |  |  | 07 Dec |  |  |  |  | 14 Dec |  |  |  |  | 21 Dec
[7 empty] | W01 |  |  |  |  | W02 |  |  |  |  | W03 |  |  |  |  | W04 |  |  |  |  | W05 |  |  |  |  | W06 |  |  |  |  | W07 |  |  |  |  | W08 |  |  |  |  | W09 |  |  |  |  | W10 |  |  |  |  | W11 |  |  |  |  | W12
WBS ID | Work package / deliverable | Owner | Start date | Finish date | Calendar days | % done | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
 | time axis 2026-10-05 to 2026-12-25
1.0 | PA1 • Vision and planning | Team | 2026-10-14 | 2026-10-20 | 7
1.5.1 | ◆ PA1 phase gate • Submit 20 Oct | Hoàng | 2026-10-20 | 2026-10-20 | 1
2.0 | PA2 • Requirements + use cases | Team | 2026-10-21 | 2026-11-02 | 13
2.4.1 | ◆ PA2 phase gate • Submit 03 Nov | Hoàng | 2026-11-03 | 2026-11-03 | 1
3.0 | PA3 • Architecture and design | Team | 2026-11-04 | 2026-11-16 | 13
3.5.1 | ◆ PA3 phase gate • Submit 17 Nov | Phúc | 2026-11-17 | 2026-11-17 | 1
4.0 | PA4 • Test planning & traceability | Team | 2026-11-18 | 2026-11-30 | 13
4.4.1 | ◆ PA4 phase gate • Submit 01 Dec | Hoàng | 2026-12-01 | 2026-12-01 | 1
5.1 | PA5 • Setup and data foundation | Minh / Phúc | 2026-12-02 | 2026-12-04 | 3
5.2 | PA5 • Auth / scheduling / rosters | Hoàng / Phúc / Minh | 2026-12-04 | 2026-12-11 | 8
5.3 | PA5 • Absence and shift coverage | Hoàng / Phúc | 2026-12-07 | 2026-12-14 | 8
5.4 | PA5 • Test automation and review | Minh / Trí | 2026-12-04 | 2026-12-15 | 12
5.5 | PA5 • Deploy / final package | Trí / Minh | 2026-12-14 | 2026-12-15 | 2
5.5.1 | ◆ PA5 phase gate • Submit 15 Dec | Trí | 2026-12-15 | 2026-12-15 | 1
6.1 | Final • Slides and rehearsal (tentative) | Team | 2026-12-16 | 2026-12-18 | 3
6.2.1 | ◆ Final presentation • Date TBD | Team |  |  | 1
7.1 | Weekly reports / meetings | Team | 2026-10-12 | 2026-12-15 | 65
7.2 | Project control / issue & PR review | Hoàng | 2026-10-15 | 2026-12-15 | 62
1
READ ME | All task dates are DRAFT proposals.
CP | ◆ Red = fixed PA gate. |  |  |  | 1
NOTE | Final due date TBD. |  |  |  | 1
1
1

## 02 Detailed WBS
SHIFTManager • Detailed WBS Gantt
Project Title | 58 WBS work packages / 351 person-hours
Project Manager | Nguyễn Huy Hoàng (Team 6)
Company Name | HCMUS • 404NotFound
Date | 2026-10-19 | [5 empty] | PA0 |  |  |  |  | PA1 | [8 empty] | PA2 | [9 empty] | PA3 | [9 empty] | PA4 | [9 empty] | PA5 | [9 empty] | Final*
[7 empty] | 05 Oct |  |  |  |  | 12 Oct |  |  |  |  | 19 Oct |  |  |  |  | 26 Oct |  |  |  |  | 02 Nov |  |  |  |  | 09 Nov |  |  |  |  | 16 Nov |  |  |  |  | 23 Nov |  |  |  |  | 30 Nov |  |  |  |  | 07 Dec |  |  |  |  | 14 Dec |  |  |  |  | 21 Dec
WBS ID | Work package / deliverable | Owner | Start date | Finish date | Calendar days | % done | W01 |  |  |  |  | W02 |  |  |  |  | W03 |  |  |  |  | W04 |  |  |  |  | W05 |  |  |  |  | W06 |  |  |  |  | W07 |  |  |  |  | W08 |  |  |  |  | W09 |  |  |  |  | W10 |  |  |  |  | W11 |  |  |  |  | W12
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
 | time axis 2026-10-05 to 2026-12-25
1.0 | PA1 • Initiation & planning
1.1.1 | Preliminary Problem Statement | Phúc | 2026-10-14 | 2026-10-15 | 2
1.1.2 | Product Position Statement | Phúc | 2026-10-16 | 2026-10-19 | 4
1.1.3 | MoSCoW priorities, scope & exclusions | Phúc | 2026-10-16 | 2026-10-19 | 4
1.1.4 | Stakeholders and user interests | Minh | 2026-10-15 | 2026-10-16 | 2
1.2.1 | C4 System Context diagram | Minh | 2026-10-16 | 2026-10-19 | 4
1.2.2 | Technology stack and operating environment | Minh | 2026-10-16 | 2026-10-19 | 4
1.3.1 | Phase gates, exit criteria, roles | Hoàng | 2026-10-15 | 2026-10-19 | 5
1.3.2 | Three-level WBS for whole project | Hoàng | 2026-10-16 | 2026-10-19 | 4
1.3.3 | Estimate work-package person-hours | Hoàng | 2026-10-19 | 2026-10-20 | 2
1.3.4 | Gantt schedule, dependencies & critical path | Trí | 2026-10-19 | 2026-10-20 | 2
1.3.5 | Human resources and project cost | Trí | 2026-10-19 | 2026-10-20 | 2
1.4.1 | Risk register, RE, mitigation and owners | Trí | 2026-10-19 | 2026-10-20 | 2
1.4.2 | Repo, board, comms and access evidence | Minh | 2026-10-15 | 2026-10-20 | 6
1.5.1 | ◆ Final review, contribution, AI log, export | Hoàng | 2026-10-20 | 2026-10-20 | 1
2.0 | PA2 • Requirements
2.1.1 | Functional requirements F01–F04 (FRs) | Phúc | 2026-10-21 | 2026-10-23 | 3
2.1.2 | NFRs, business rules & acceptance criteria | Trí | 2026-10-21 | 2026-10-26 | 6
2.2.1 | Actors, Use Case diagram | Phúc | 2026-10-23 | 2026-10-27 | 5
2.2.2 | Use Case specifications incl exceptions | Hoàng | 2026-10-27 | 2026-10-30 | 4
2.3.1 | UI mockups and screen flows | Minh | 2026-10-22 | 2026-10-29 | 8
2.3.2 | Traceability and review issue log | Trí | 2026-10-30 | 2026-11-02 | 4
2.4.1 | ◆ SRS final review, contribution, AI log | Hoàng | 2026-11-02 | 2026-11-03 | 2
3.0 | PA3 • Design
3.1.1 | C4 Container, Component, Deployment | Minh | 2026-11-04 | 2026-11-09 | 6
3.1.2 | At least 3 ADRs with justification | Hoàng | 2026-11-09 | 2026-11-12 | 4
3.2.1 | Class diagram & class specs | Phúc | 2026-11-05 | 2026-11-10 | 6
3.2.2 | Sequence & State diagrams | Hoàng | 2026-11-10 | 2026-11-13 | 4
3.3.1 | ERD and normalized schema | Trí | 2026-11-05 | 2026-11-10 | 6
3.3.2 | Constraints, table specs & indexes | Trí | 2026-11-10 | 2026-11-12 | 3
3.4.1 | Screen specs, flow, accessibility checklist | Minh | 2026-11-09 | 2026-11-13 | 5
3.5.1 | ◆ Design/SRS traceability review & finalize PA3 | Phúc | 2026-11-16 | 2026-11-17 | 2
4.0 | PA4 • Test planning
4.1.1 | Test Plan, environment, entry/exit, defect process | Phúc | 2026-11-18 | 2026-11-23 | 6
4.2.1 | Equivalence Partitioning and BVA design | Hoàng | 2026-11-23 | 2026-11-26 | 4
4.2.2 | Decision tables for scheduling and absence/coverage rules | Minh | 2026-11-23 | 2026-11-26 | 4
4.3.1 | Detailed test cases for F01–F04 | Trí | 2026-11-25 | 2026-11-30 | 6
4.3.2 | Requirements–test traceability review | Minh | 2026-11-27 | 2026-11-30 | 4
4.4.1 | ◆ Final test plan review, contribution & AI log | Hoàng | 2026-11-30 | 2026-12-01 | 2
5.0 | PA5 • Implementation & testing
5.1.1 | Create React/Express project and local dev config | Minh | 2026-12-02 | 2026-12-04 | 3
5.1.2 | Supabase schema, migrations, employee profiles, skills, availability, shift data and test data | Phúc | 2026-12-02 | 2026-12-04 | 3
5.2.1 | Supabase Auth, JWT verification and Employee/Manager/Boss authorization (F01) | Hoàng | 2026-12-04 | 2026-12-08 | 5
5.2.2 | Constraint-based automatic scheduling and fairness scoring (F02) | Phúc | 2026-12-04 | 2026-12-09 | 6
5.2.3 | Published roster, change indicators, acknowledgement and Boss overview (F03) | Minh | 2026-12-08 | 2026-12-11 | 4
5.2.4 | Manager roster preview, manual adjustment and publishing (F02) | Hoàng | 2026-12-09 | 2026-12-11 | 3
5.3.1 | Employee absence submission and manager no-show recording (F04) | Hoàng | 2026-12-07 | 2026-12-10 | 4
5.3.2 | Replacement eligibility checks and substitute acceptance (F04) | Phúc | 2026-12-09 | 2026-12-11 | 3
5.3.3 | Manager coverage decision and consistent roster update (F04) | Hoàng | 2026-12-11 | 2026-12-14 | 4
5.3.4 | Integrate absence/coverage workflow UI with REST API (F04) | Phúc | 2026-12-11 | 2026-12-14 | 4
5.4.1 | Unit tests and coverage report | Minh | 2026-12-08 | 2026-12-14 | 7
5.4.2 | Automated cases (2 use cases × 2 scenarios), PR CI | Trí | 2026-12-04 | 2026-12-14 | 11
5.4.3 | Test execution, defect fixes and PR reviews | Trí | 2026-12-11 | 2026-12-15 | 5
5.5.1 | ◆ Deploy and verify live demo | Trí | 2026-12-14 | 2026-12-15 | 2
5.5.2 | Demo video, implementation report, retrospective | Minh | 2026-12-14 | 2026-12-15 | 2
6.0 | Final • Preparation (date TBD)
6.1.1 | Prepare slides and project summary | Minh | 2026-12-16 | 2026-12-17 | 2
6.1.2 | Demo script + practice all speakers | Trí | 2026-12-17 | 2026-12-18 | 2
6.2.1 | Final demo and presentation | Hoàng
7.0 | Continuous project management
7.1.1 | Weekly status meetings W02–W10 | Hoàng | 2026-10-12 | 2026-12-15 | 65
7.1.2 | Weekly Status Report W03 | Phúc | 2026-10-19 | 2026-10-20 | 2
7.1.3 | Weekly reports W02 and W04–W10 (8 reports) | Phúc | 2026-10-12 | 2026-12-15 | 65
7.2.1 | Maintain GitHub task board | Hoàng | 2026-10-15 | 2026-12-15 | 62
7.2.2 | Git/PR reviews, risks, baselines, change records | Hoàng | 2026-10-15 | 2026-12-15 | 62

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.

## 03 Dependencies
SHIFTManager ¦ Proposed dependencies and phase-gate critical sequence
Source: PA1-ProjectProposal-Plan(3).docx • WBS/effort; start/finish and predecessors are planning proposals, not approved facts.
Critical = phase-gate sequence only; complete task-level CPM and resource leveling require team validation.
WBS ID | Work package | Owner | PA/Stream | Effort (h) | Predecessors (proposed) | Start (draft) | Finish (draft) | Critical gate
1.1.1 | Preliminary Problem Statement | Phúc | PA1 | 3 | — | 2026-10-14 | 2026-10-15
1.1.2 | Product Position Statement | Phúc | PA1 | 2 | 1.1.1 | 2026-10-16 | 2026-10-19
1.1.3 | MoSCoW priorities, scope & exclusions | Phúc | PA1 | 3 | 1.1.1 | 2026-10-16 | 2026-10-19
1.1.4 | Stakeholders and user interests | Minh | PA1 | 1.5 | — | 2026-10-15 | 2026-10-16
1.2.1 | C4 System Context diagram | Minh | PA1 | 3 | — | 2026-10-16 | 2026-10-19
1.2.2 | Technology stack and operating environment | Minh | PA1 | 2 | — | 2026-10-16 | 2026-10-19
1.3.1 | Phase gates, exit criteria, roles | Hoàng | PA1 | 1.5 | — | 2026-10-15 | 2026-10-19
1.3.2 | Three-level WBS for whole project | Hoàng | PA1 | 3.5 | 1.1.1 | 2026-10-16 | 2026-10-19
1.3.3 | Estimate work-package person-hours | Hoàng | PA1 | 3 | 1.3.2 | 2026-10-19 | 2026-10-20
1.3.4 | Gantt schedule, dependencies & critical path | Trí | PA1 | 4 | 1.3.2, 1.3.3 | 2026-10-19 | 2026-10-20
1.3.5 | Human resources and project cost | Trí | PA1 | 2 | 1.3.3 | 2026-10-19 | 2026-10-20
1.4.1 | Risk register, RE, mitigation and owners | Trí | PA1 | 4 | — | 2026-10-19 | 2026-10-20
1.4.2 | Repo, board, comms and access evidence | Minh | PA1 | 2.5 | — | 2026-10-15 | 2026-10-20
1.5.1 | Final review, contribution, AI log, export | Hoàng | PA1 | 2 | 1.1.3, 1.2.1, 1.3.4, 1.3.5, 1.4.1, 1.4.2 | 2026-10-20 | 2026-10-20 | YES
2.1.1 | Functional requirements F01–F04 (FRs) | Phúc | PA2 | 6 | 1.5.1 | 2026-10-21 | 2026-10-23
2.1.2 | NFRs, business rules & acceptance criteria | Trí | PA2 | 7 | — | 2026-10-21 | 2026-10-26
2.2.1 | Actors, Use Case diagram | Phúc | PA2 | 4 | 2.1.1 | 2026-10-23 | 2026-10-27
2.2.2 | Use Case specifications incl exceptions | Hoàng | PA2 | 10 | 2.2.1 | 2026-10-27 | 2026-10-30
2.3.1 | UI mockups and screen flows | Minh | PA2 | 10 | 2.1.1 | 2026-10-22 | 2026-10-29
2.3.2 | Traceability and review issue log | Trí | PA2 | 5 | 2.2.2, 2.3.1 | 2026-10-30 | 2026-11-02
2.4.1 | SRS final review, contribution, AI log | Hoàng | PA2 | 4 | 2.1.2, 2.2.2, 2.3.2 | 2026-11-02 | 2026-11-03 | YES
3.1.1 | C4 Container, Component, Deployment | Minh | PA3 | 7 | 2.4.1 | 2026-11-04 | 2026-11-09
3.1.2 | At least 3 ADRs with justification | Hoàng | PA3 | 5 | 3.1.1 | 2026-11-09 | 2026-11-12
3.2.1 | Class diagram & class specs | Phúc | PA3 | 7 | 2.4.1 | 2026-11-05 | 2026-11-10
3.2.2 | Sequence & State diagrams | Hoàng | PA3 | 10 | 3.2.1 | 2026-11-10 | 2026-11-13
3.3.1 | ERD and normalized schema | Trí | PA3 | 7 | 2.4.1 | 2026-11-05 | 2026-11-10
3.3.2 | Constraints, table specs & indexes | Trí | PA3 | 5 | 3.3.1 | 2026-11-10 | 2026-11-12
3.4.1 | Screen specs, flow, accessibility checklist | Minh | PA3 | 6 | 2.3.1 | 2026-11-09 | 2026-11-13
3.5.1 | Design/SRS traceability review & finalize PA3 | Phúc | PA3 | 4 | 3.1.2, 3.2.2, 3.3.2, 3.4.1 | 2026-11-16 | 2026-11-17 | YES
4.1.1 | Test Plan, environment, entry/exit, defect process | Phúc | PA4 | 8 | 3.5.1 | 2026-11-18 | 2026-11-23
4.2.1 | Equivalence Partitioning and BVA design | Hoàng | PA4 | 8 | 4.1.1 | 2026-11-23 | 2026-11-26
4.2.2 | Decision tables for scheduling and absence/coverage rules | Minh | PA4 | 6 | 4.1.1 | 2026-11-23 | 2026-11-26
4.3.1 | Detailed test cases for F01–F04 | Trí | PA4 | 11 | 4.2.1, 4.2.2 | 2026-11-25 | 2026-11-30
4.3.2 | Requirements–test traceability review | Minh | PA4 | 4 | 4.3.1 | 2026-11-27 | 2026-11-30
4.4.1 | Final test plan review, contribution & AI log | Hoàng | PA4 | 3 | 4.3.1, 4.3.2 | 2026-11-30 | 2026-12-01 | YES
5.1.1 | Create React/Express project and local dev config | Minh | PA5 | 7 | 4.4.1 | 2026-12-02 | 2026-12-04
5.1.2 | Supabase schema, migrations, employee profiles, skills, availability, shift data and test data | Phúc | PA5 | 7 | 3.3.2 | 2026-12-02 | 2026-12-04
5.2.1 | Supabase Auth, JWT verification and Employee/Manager/Boss authorization (F01) | Hoàng | PA5 | 10 | 5.1.1, 5.1.2 | 2026-12-04 | 2026-12-08
5.2.2 | Constraint-based automatic scheduling and fairness scoring (F02) | Phúc | PA5 | 10 | 5.1.2 | 2026-12-04 | 2026-12-09
5.2.3 | Published roster, change indicators, acknowledgement and Boss overview (F03) | Minh | PA5 | 8 | 5.2.1, 5.2.2 | 2026-12-08 | 2026-12-11
5.2.4 | Manager roster preview, manual adjustment and publishing (F02) | Hoàng | PA5 | 8 | 5.2.2, 5.2.1 | 2026-12-09 | 2026-12-11
5.3.1 | Employee absence submission and manager no-show recording (F04) | Hoàng | PA5 | 8 | 5.2.1 | 2026-12-07 | 2026-12-10
5.3.2 | Replacement eligibility checks and substitute acceptance (F04) | Phúc | PA5 | 7 | 5.3.1 | 2026-12-09 | 2026-12-11
5.3.3 | Manager coverage decision and consistent roster update (F04) | Hoàng | PA5 | 13 | 5.3.2, 5.2.4 | 2026-12-11 | 2026-12-14
5.3.4 | Integrate absence/coverage workflow UI with REST API (F04) | Phúc | PA5 | 9 | 5.3.1, 5.3.2 | 2026-12-11 | 2026-12-14
5.4.1 | Unit tests and coverage report | Minh | PA5 | 10 | 5.2.1, 5.2.2 | 2026-12-08 | 2026-12-14
5.4.2 | Automated cases (2 use cases × 2 scenarios), PR CI | Trí | PA5 | 10 | 5.1.1 | 2026-12-04 | 2026-12-14
5.4.3 | Test execution, defect fixes and PR reviews | Trí | PA5 | 12 | 5.2.3, 5.3.3, 5.3.4, 5.4.1, 5.4.2 | 2026-12-11 | 2026-12-15
5.5.1 | Deploy and verify live demo | Trí | PA5 | 6 | 5.4.3 | 2026-12-14 | 2026-12-15 | YES
5.5.2 | Demo video, implementation report, retrospective | Minh | PA5 | 6 | 5.4.3, 5.5.1 | 2026-12-14 | 2026-12-15
6.1.1 | Prepare slides and project summary | Minh | Final | 4 | 5.5.1 | 2026-12-16 | 2026-12-17
6.1.2 | Demo script + practice all speakers | Trí | Final | 5 | 6.1.1 | 2026-12-17 | 2026-12-18
6.2.1 | Final demo and presentation | Hoàng | Final | 2 | 6.1.2
7.1.1 | Weekly status meetings W02–W10 | Hoàng | Mgmt | 9 | — | 2026-10-12 | 2026-12-15
7.1.2 | Weekly Status Report W03 | Phúc | Mgmt | 2 | 1.3.1 | 2026-10-19 | 2026-10-20
7.1.3 | Weekly reports W02 and W04–W10 (8 reports) | Phúc | Mgmt | 16 | — | 2026-10-12 | 2026-12-15
7.2.1 | Maintain GitHub task board | Hoàng | Mgmt | 4 | — | 2026-10-15 | 2026-12-15
7.2.2 | Git/PR reviews, risks, baselines, change records | Hoàng | Mgmt | 4 | 7.2.1 | 2026-10-15 | 2026-12-15
PHASE-GATE CHAIN | Gate WBS | Submission | Due (fixed) | Predecessor gate | Gate-level critical? | Reference
PA1 | 1.5.1 | ◆ PA submission | 2026-10-20 | Start / initial work | YES | Fixed team deadline
PA2 | 2.4.1 | ◆ PA submission | 2026-11-03 | 1.5.1 | YES | Fixed team deadline
PA3 | 3.5.1 | ◆ PA submission | 2026-11-17 | 2.4.1 | YES | Fixed team deadline
PA4 | 4.4.1 | ◆ PA submission | 2026-12-01 | 3.5.1 | YES | Fixed team deadline
PA5 | 5.5.1 | ◆ PA submission | 2026-12-15 | 4.4.1 | YES | Fixed team deadline
Proposed gate chain: PA1 → PA2 → PA3 → PA4 → PA5; Final presentation date remains TBD.

## 04 Assumptions
SHIFTManager ¦ Timeline assumptions, scope and effort check
Planning input | Value
PA1 due | 2026-10-20
PA2 due | 2026-11-03
PA3 due | 2026-11-17
PA4 due | 2026-12-01
PA5 due | 2026-12-15
Final presentation date | TBD – do not treat draft prep as official due date
Timeline shown | Mon–Fri, 05 Oct – 25 Dec 2026 (12 weeks)
Date validity | PA deadlines supplied by the team; task dates proposed, not approved
Dependency validity | Predecessors are a planning draft; overlapping tasks may exchange partial drafts
PA/Stream | Effort (person-h) | Share of total | Capacity assumption | Action
PA1 | 37 | 10.54% |  | Retrospective plan – validate actual work dates
PA2 | 46 | 13.11% |  | Two-week gate, proposed dates
PA3 | 51 | 14.53% |  | Two-week gate, proposed dates
PA4 | 40 | 11.4% |  | Two-week gate, proposed dates
PA5 | 131 | 37.32% | Provisional: 4 people × 16 h/week × 2 weeks = 128h | 131 hours across four members in two weeks – capacity check needed
Final | 11 | 3.134% |  | Final due date TBD; prep dates tentative
Mgmt | 35 | 9.972% |  | Continuous workload spread across PA1–PA5
TOTAL | 351 | 100%
Important scope note
F01 authentication/roles, F02 automatic scheduling, F03 roster acknowledgement, F04 absence/coverage.
C4 initial diagram may be revised in later PAs according to TA; this Gantt uses the current four-feature scope.
Planned task dates are recommendations generated for the team, not historic evidence or contractual due dates.
Calendar dates exclude weekend work, but do not model public holidays, personal availability or strict resource levelling.
Only phase-gate critical chain is identified; task-level critical path must be verified by Trí with dependencies and duration.
Project work packages / hours from user-supplied PA1 (3).docx; official template structure from uploaded workbook.

## 05 Weekly Gantt
SHIFTManager ¦ 12-week project Gantt overview
Scope: F01 Auth • F02 Auto schedule • F03 Roster • F04 Absence ¦ source: PA1 (3)
Draft work-package dates; official PA due dates fixed by team. Red marks phase submissions. Final due TBD.
WBS | Workstream / milestone | Owner | Start | Due | Duration (days) | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12
[6 empty] | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
1.0 | PA1 • Vision and planning | Team | 2026-10-14 | 2026-10-20 | 7
1.5.1 | ◆ PA1 phase gate • Submit 20 Oct | Hoàng | 2026-10-20 | 2026-10-20 | 1
2.0 | PA2 • Requirements + use cases | Team | 2026-10-21 | 2026-11-02 | 13
2.4.1 | ◆ PA2 phase gate • Submit 03 Nov | Hoàng | 2026-11-03 | 2026-11-03 | 1
3.0 | PA3 • Architecture and design | Team | 2026-11-04 | 2026-11-16 | 13
3.5.1 | ◆ PA3 phase gate • Submit 17 Nov | Phúc | 2026-11-17 | 2026-11-17 | 1
4.0 | PA4 • Test planning & traceability | Team | 2026-11-18 | 2026-11-30 | 13
4.4.1 | ◆ PA4 phase gate • Submit 01 Dec | Hoàng | 2026-12-01 | 2026-12-01 | 1
5.1 | PA5 • Setup and data foundation | Minh / Phúc | 2026-12-02 | 2026-12-04 | 3
5.2 | PA5 • Auth / scheduling / rosters | Hoàng / Phúc / Minh | 2026-12-04 | 2026-12-11 | 8
5.3 | PA5 • Absence and shift coverage | Hoàng / Phúc | 2026-12-07 | 2026-12-14 | 8
5.4 | PA5 • Test automation and review | Minh / Trí | 2026-12-04 | 2026-12-15 | 12
5.5 | PA5 • Deploy / final package | Trí / Minh | 2026-12-14 | 2026-12-15 | 2
5.5.1 | ◆ PA5 phase gate • Submit 15 Dec | Trí | 2026-12-15 | 2026-12-15 | 1
6.1 | Final • Slides and rehearsal (tentative) | Team | 2026-12-16 | 2026-12-18 | 3
6.2.1 | ◆ Final presentation • Date TBD | Team
7.1 | Weekly reports / meetings | Team | 2026-10-12 | 2026-12-15 | 65
7.2 | Project control / issue & PR review | Hoàng | 2026-10-15 | 2026-12-15 | 62
Critical chain (phase gates): 1.5.1 → 2.4.1 → 3.5.1 → 4.4.1 → 5.5.1 (task-level CPM pending review).
* Final presentation date TBD; week-to-week resource feasibility, dependencies and task dates are still proposed.