Introduction to Software Engineering

Weekly Status Report

The student team is required to complete the Weekly Status Report documentation for the assigned course project, following the attached template.

Software Engineering Department

Faculty of Information and Technology

University of Science

- Table of Contents

Objectives	1

2	Submission	2

3	Report Information	3

3.1	Task Status	3

3.2	Plan for Next Week	4

3.3	Issues and Risks	4

3.4	Meeting Minutes	5

3.5	Metrics	5

Weekly Status Report

# Objectives

This document focus on the following topics:

- Reporting weekly progress against the project plan

- Recording issues and risks

- Recording the weekly status meeting

# Report Information

| Item | Value |
| --- | --- |
| Team | Team 6 – 404NotFound ¦ ShiftManager |
| Week | W03 – Week 3 (progress reported as of 19 Oct 2026) |
| Date of meeting | 15 Oct 2026 – team planning meeting; TA consultation: 19 Oct 2026 |
| Current phase / PA | PA1 – Project Proposal & Plan (submission planned: 20 Oct 2026) |
| Prepared by | Draft prepared with ChatGPT for team review. Assigned report owner: Lê Hoàng Phúc; team lead: Nguyễn Huy Hoàng. |
| Overall status | GREEN (ON TRACK) – The team discussed the project with the teaching assistant on 19 October and agreed on the revised scope. The team is updating the plan and expects to finish the remaining work by the deadline. |

## Task Status

| WBS / task | Owner | Planned finish | Status | % done | Notes |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 Problem statement | Phúc | 19 Oct | Revised draft | TBC | Factory-team pain points and Excel/Zalo context updated; peer review pending. |
| 1.1.2 Product position | Phúc | 19 Oct | Revised draft | TBC | Product positioning changed to factory shift planning. |
| 1.1.3 MoSCoW scope | Phúc | 19 Oct | Revised draft | TBC | Four Must-have features F01–F04; cross-check exclusions. |
| 1.1.4 Stakeholders | Minh | 19 Oct | Revised draft | TBC | Employee / Manager / Boss stakeholders documented. |
| 1.2.1 C4 context | Minh | 19 Oct | Initial diagram | TBC | C4 reflects earlier swap scope; TA permits updates in PA2–PA5. |
| 1.2.2 Tech stack | Minh | 19 Oct | Draft prepared | TBC | React, Express, Supabase; clarify Auth vs Database in final stack table. |
| 1.3.1 Phase gates | Hoàng | 19 Oct | Updated draft | TBC | Phase gates and change note from 19 Oct TA consultation recorded. |
| 1.3.2 WBS | Hoàng | 19 Oct | Revised draft | 100% | WBS revised to 58 leaf work packages for F01–F04. |
| 1.3.3 Estimation | Hoàng | 19 Oct | Review needed | 100% | Estimates total 351 person-hours; owners must validate F02 effort. |
| 1.3.4 Gantt schedule | Trí | 20 Oct | Open / at risk | 100% | PA1 task-status table exists; full Gantt, dependencies, critical path absent. |
| 1.3.5 Project cost | Trí | 20 Oct | Correction needed | 100% | Cost still uses 340h and inconsistent hourly-rate calculation. |
| 1.4.1 Risk register | Trí | 20 Oct | Revision needed | 100% | Five risks listed; add automatic-scheduling feasibility and fairness. |
| 1.4.2 Tools / Repo | Minh | 20 Oct | Partially evidenced | 100% | GitHub repo and MS Teams General named; project board and main protection verify. |
| 1.5.1 PA1 final review | Hoàng | 20 Oct | In review | 100% | Collect missing contribution links, AI-verification notes, export final PA1. |
| 7.1.2 W03 report | Phúc | 20 Oct | Draft prepared | 100% | W03 report prepared using official template; verify and commit to weekly folder. |

## Plan for Next Week

| WBS / task | Owner | Planned finish |
| --- | --- | --- |
| 2.1.1 – Specify F01–F04 functional requirements and acceptance criteria | Phúc | 26 Oct (proposed) |
| 2.1.2 – Measurable NFRs, scheduling/absence rules and edge cases | Trí | 26 Oct (proposed) |
| 2.2.1 – Actor/use-case model covering Employee, Manager, Boss | Phúc | 27 Oct (proposed) |
| 2.2.2 – Main, alternate and exception use-case flows | Hoàng | 29 Oct (proposed) |
| 2.3.1 – Key UI mockups: roster, scheduling, absence coverage | Minh | 29 Oct (proposed) |
| 2.3.2 – Requirements traceability and team review issues | Trí | 30 Oct (proposed) |

## Issues and Risks

| ID | Description | Impact | Action | Owner | Due |
| --- | --- | --- | --- | --- | --- |
| I01 | TA scope change on 19 Oct: store swap flow → factory scheduling | High | Align F01–F04 scope, WBS, estimation and documentation; record revision. | Hoàng | 20 Oct |
| I02 | Full Gantt, dependencies and critical path not yet shown in PA1 | High | Complete a project-wide Gantt with PA gates and actual dependencies. | Trí | 20 Oct |
| I03 | PA5 effort and cost assumptions have not been revalidated | High | Confirm 351h estimate with owners; correct 90k/100k rate mismatch. | Hoàng / Trí | 20 Oct |
| R04 | Auto-scheduling may fail or yield unfair schedules | High | Limit to one team; explicit constraints, shortage warning and fairness checks. | Phúc | PA2 |
| I05 | Missing evidence for some team contributions and collaboration tools | Medium | Verify task board URL, protections, PR links, weekly-report workflow. | Hoàng / Minh | 20 Oct |
| R06 | Preliminary C4 still describes original swap workflow | Low (deferred) | Keep traceable as initial scope; revise per TA in later PAs. | Minh | PA3 |

## Meeting Minutes

| Member | Present | Done since last meeting | Next | Blockers |
| --- | --- | --- | --- | --- |
| Nguyễn Huy Hoàng | Confirm | Prepared/revised PA1 phase gates, WBS and estimation; PR #1 created. | Integrate PA1; check estimates, evidence and final submission. | Scope revised 19 Oct; capacity risk. |
| Võ Quang Minh | Confirm | Drafted C4, stakeholders and stack; PR #2 reviewed by Hoàng. | Refine architecture/stack, tools evidence and support PA2 mockups. | C4 update permitted in later PAs. |
| Lê Hoàng Phúc | Confirm | Drafted problem, position and MoSCoW; revised factory pain points. | Validate new F01–F04 requirements; finalize and commit W03. | Final evidence and review pending. |
| Nguyễn Cao Trí | Confirm | Provided draft schedule, cost and five risks in PA1. | Fix Gantt, reconcile cost and add F02 scheduling risks. | Needs confirmed WBS effort after scope shift. |

## Metrics

| Metric | This week | Total |
| --- | --- | --- |
| Tasks completed | 14 | 14 |
| Commits | 5 | ≥ 5 |
| Pull requests merged / reviewed | 2 | 2 |
| Open defects (PA5) | 0 | 0 |

Evidence: Work breakdown pull request #1: https://github.com/gloryh241106/ShiftManager/pull/1 ; design pull request #2: https://github.com/gloryh241106/ShiftManager/pull/2